## Bug_issue
Project Name | martaarcadu // FO11A4A362D87 |  | Issue Start Date | 2025-06-26 | Test Result: | Fixed | Not Fixed | In Progress | Won't Fix | Report | 🐞 Bug remain Rate: 21.21%
Operating System | Android ¦¦ Figma |  | Issue End Date | On-going |  | 31 | 2 | 0 | 0
Brower/ Device | Android Emmulator: Pixel 9 Pro API 36 ¦¦ Realme c17 |  | Test Case Developed By | Md Abdur Rahaman Tutul | [6 empty] | ✅ Bug Fix Rate: 69.70%
⌛ Not Implemented: 3.03%
Sprint |  |  | Developer and Reviewed By | Anik Biswas | Total: | 33 |  |  |  |  | 🛠️ Need Improvement: 6.06%
Bug ID | Module | Feature | Bug Type | Bug Title | Bug Description | Steps to Reproduce | Actual Result | Expected Result | Issue Labels | Severity | Attatchment | Dev_Status | Testers | Remark | Re-tesing | Date
B_ID_001 | Onboarding Screen | First-time Setup | Flutter_UI | Onboarding screen shows every time | Onboarding screen appears every time user opens the app, even after completing it once. | 1. Open the app 2. Complete the onboarding 3. Close the app 4. Open again | Onboarding screen appears again | Onboarding should appear only on first launch or until completed | Bug_Fixed | Average | Video Link | Fixed | Tutul |  |  | 2025-06-26
B_ID_002 | Forget password | OTP Verification > resend code | Flutter_UI | Resend Code Not Clickable | On the Reset Password screen, the "Resend Code" option is visible but not interactive or redirecting anywhere. | 1. Open the app 2. Go to "Forgot Password" 3. Submit email 4. On OTP screen, observe the "Resend Code" link/button | "Resend Code" is not clickable and does nothing | "Resend Code" should be tappable and trigger the resend OTP API or feedback | Bug_Fixed | Major | Screen Shot | Fixed |  |  |  | 2025-06-26
B_ID_003 |  | New Password | Flutter_UI | Password field label incorrect on Reset screen | The password input field on the “New Password” screen shows label as “Password” instead of “New Password” | 1. Open the mobile app 2. Tap “Forgot Password” 3. Enter email and verify OTP 4. Navigate to “New Password” page | Label shows “Password” instead of “New Password” | Label should say “New Password” for clarity | Bug_Fixed | Minor | Screen Shot | Fixed |  | Affects user clarity and design consistency |  | 2025-06-26
B_ID_004 | Login | Login Tab resposive | Flutter_UI | Not responsive on small screens or any device | The “Don’t have an account? Create Account” text is not properly visible on smaller screens; requires scrolling. | 1. Open the mobile app 2. Navigate to the Login tab 3. Observe the bottom content on small-screen devices | Bottom text requires manual scroll to view; UI not responsive | Bottom content should be visible without manual scroll and responsive | Bug_Fixed | Average | Video Link | Fixed |  |  |  | 2025-06-26
B_ID_005 |  | Create Account link | Flutter_UI | Not redirect any tab | In the Create account functionality or tab, not route any tab | 1. Open the mobile app 2. Navigate to the Login tab 3. Observe the creacte account | Not redirect any tab | The link should clickable and redirect the registration tab | Bug_Fixed | Critical | Screen Shot | Fixed |  |  |  | 2025-06-26
B_ID_006 | Home Tab | Footer UI | Flutter_UI | Floating (+) button partially hidden | The “+” action button in the footer is cut off or not fully visible on mobile. | 1. Open the mobile app 2. Go to Home tab 3. Observe the footer section | The “+” button appears partially off-screen or clipped | The “+” button should be fully visible and properly centered | Bug_Fixed | Minor | Screen Shot | Fixed |  |  |  | 2025-06-26
B_ID_007 |  | My Active Service> Details | Flutter_UI, Flutter_Functional | 3 Dot menu dot implement tab | In the home's My active service card redirect the details tab have 3 dot manu which is not redirect and option | 1. Open the app 2. Home tab to My active service 3. rediret the details obser the 3 dot manu | 3 Dot menu dot implement tab | The 3 dot manu should have edit and delete functionality | Bug_Fixed | Major | Screen Shot | Fixed |  |  |  | 2025-06-26
B_ID_008 |  |  | Flutter_UI | Header text not match as per requirement | In the home's My active service card redirect the details tab have "Post a request" instead of " Request details" | 1. Open the app 2. Home tab to "My Active service card 3. Observe the header text | Header text not match as per requirement | My active service card detalls should have the header text "Request details" | Bug_Fixed | Minor | Screen Shot | Fixed |  |  |  | 2025-06-26
B_ID_009 |  | My product > See ALL | Flutter_UI | See All not redirect | In the My product card, the See all not redirect or not open the all list | 1. Open the mobile app 2. Go to Home tab 3. Observe and click "My Product" See all | See All not redirect | In the My product card, the See all Should redirect and open the all list | Bug_Fixed | Average | Screen Shot | Fixed |  | figma design has been updated sience then and will not be available in sell all |  | 2025-06-26
B_ID_010 |  | Navigation Drawer | Flutter_UI | Sub Tab Overlaps with Footer Tab | When a user taps the burger menu and navigates to a sub tab, the tab is hidden behind the footer. | 1. Open the mobile app 2. Go to the Home tab 3. Tap the burger menu icon 4. Navigate to any sub tab 5. Observe the opened sub tab view | Sub tab content is partially hidden by the footer tab | Sub tab should open fully above the footer tab without being hidden | Bug_Fixed | Minor | Screen Shot | Fixed |  |  |  | 2025-06-26
B_ID_011 |  | Navigation Drawer > Edit | Flutter_Functional | Edit icon not functioning | the burger menu, the profile edit icon not redirect and functining for edit profile details | 1. Open the mobile app 2. Go to the Home tab 3. Tap the burger menu icon 4. Click the Edit icon and observe | Edit icon not functioning | The profile edit icon should redirect and functining for edit profile details | Bug_Fixed | Critical | Screen Shot | Fixed |  | figma design has been updated sience then and will not be available in sell all |  | 2025-06-26
B_ID_012 |  | Navigation Drawer > Log Out | Flutter_Functional | Log Out not functioning | The burger menu, the Log Out manu not redirect and functioning for edit profile details | 1. Open the mobile app 2. Go to the Home tab 3. Tap the burger menu icon 4. Click the Log Out Manu and observe | Log Out not functioning | The profile logout should redirect and functioning for logout the user | Bug_Fixed | Average | Screen Shot | Fixed |  |  |  | 2025-06-26
B_ID_013 |  | Post a Service/ Post a product | Flutter_Functional | Budget & Response Time Accept Any Value | The form fields "Your Budget" and "Response Time" (Day, Hour, Minute) accept invalid inputs | 1. Go to Home tab 2. Tap on "Post a Service" and "Post a product" 3. Enter negative or non-numeric values in "Budget" or "Response Time" fields 4. Submit the form | No error message shown; invalid values are accepted and submitted | Input validation should restrict invalid entries and show appropriate error messages | Bug_Fixed | Average | Video link | Fixed |  |  |  | 2025-06-26
B_ID_014 |  |  | Flutter_UI | "Response Time" (Day, Hour, Minute) error handeling message not show poperly | "Response Time" (Day, Hour, Minute) error handeling message not visibale properly and text not fully visible | 1. Go to Home tab 2. Tap on "Post a Service" and "Post a product" 3. Enter negative or non-numeric values in "Budget" or "Response Time" fields 4. Submit the form | "Response Time" (Day, Hour, Minute) error handeling message not show poperly | "Response Time" (Day, Hour, Minute) error handeling message should show poperly | Improvements | Minor | Screen shot | Fixed |  | Re-testingis not a bug vaidator text big thai's why please enter number....... |  | 2025-06-28
B_ID_015 |  |  | Flutter_Functional, Flutter_UI | Post another request not redirect | The form fields after successfully tab, there have post another request not redirect | 1. Go to Home tab 2. Tap on "Post a Service" and "Post a product" 4. Submit the form 5. Observe the post another request | Post another request not redirect | Should allow to redirect another post | Bug_Fixed | Average | Screen shot | Fixed |  |  |  | 2025-06-26
B_ID_016 | Home> Menu bar> Reliablility | Reliablity tab responsive | Flutter_UI | Not responsive on small screens or any device | Content is not properly visible on smaller screens; requires scrolling | 1. Open the app 2. Go to the reliabity tab and oberse the responsive | Bottom text requires manual scroll to view; UI not responsive | Bottom content should be visible without manual scroll and responsive | Bug_Fixed | Minor | Video lInk | Fixed |  | it's not an issue. it will be scrollable |  | 2025-06-26
B_ID_017 |  | Identity Verified | Flutter_Functional | Full Name & DOB fields accept invalid input | Full Name and Date of Birth fields allow any string, no validation | 1. Open the mobile app 2. Tap on Home tab 3. Open burger menu 4. Go to “Reliability” > “Verify Your Identity” 5. Enter invalid input in Full Name and DOB fields | Fields accept any type of string (e.g., symbols, numbers in name, random text in DOB) | Full Name should only accept letters; DOB should follow date format validation (e.g., DD/MM/YYYY) | Bug | Average | Video Link | Fixed |  | Full name filed still not fixed Please see: Video link | Fixed | 2025-06-26
B_ID_018 |  | Identity Verified > ID field | Flutter_Functional | Validation Error for ID Field | National ID/Passport input field shows phone number validation | 1. Open the mobile app and go to Home tab 2. Tap burger menu 3. Select “Reliability Redirect” 4. Tap “Verify Your Identity” 5. Enter a valid National ID or Passport number in the input field | Validation error message: “Enter a valid phone number”; field only accepts 10-digit numbers | Should accept valid National ID or Passport numbers; proper validation for ID/Passport required | Bug_Fixed | Average | Video Link | Fixed |  |  |  | 2025-06-26
B_ID_019 |  | Identity Verified > Optional | Flutter_Functional | Optional field throwing validation | "Additional Notes (optional)" field incorrectly triggers a validation error when left empty. | 1. Open the mobile app. 2. Go to the Home tab. 3. Tap the burger menu. 4. Navigate to Reliability > Verify Your Identity. 5. Leave the "Additional Notes (optional)" field empty. | A validation error appears: “Please enter your information.” | The form should be submitted successfully, as the "Additional Notes" field is marked optional. | Bug | Average | Screen shot | Fixed |  | Still not fixed | Fixed | 2025-06-26
B_ID_020 |  | Identity Verified > Upload ID Document | Flutter_UI | Upload ID Document card pading mismatch | Upload ID Document card pading mismatch form other relative card | 1. Open the mobile app. 2. Go to the Home tab. 3. Tap the burger menu. 4. Navigate to Reliability > Verify Your Identity. 5. Observe the padding of upload ID Document Card | Upload ID Document card pading mismatch | Upload ID Document card padding the should be match form other relative card | Bug_Fixed | Minor | Screen shot | Fixed |  |  |  | 2025-06-26
B_ID_021 |  |  | Flutter_Functional | File type validation not enforced | upload field allows any file type, even those not listed (e.g., .exe, .txt), and doesn't show an error message for unsupported formats. | 1. Open the mobile app 2. Navigate to Home Tab → Burger Menu → Reliability → Verify your identity 3. Tap "Upload ID Document" 4. Upload an invalid file (e.g., .zip) | File uploads successfully regardless of type; no validation error shown. | Only PDF, JPG, or PNG files should be allowed; invalid file types should trigger an error message. | Bug_Fixed | Major | Video link | Fixed |  |  |  | 2025-06-26
B_ID_022 |  |  | Flutter_UI | Uploaded file path displayed improperly | After uploading ID Document, the full device file path is shown, which is not user-friendly and may cause confusion or concern | 1. Open the app 2. Go to Home Tab 3. Tap burger menu > Reliability > Verify your identity 4. Tap “Upload ID Document” and select a file 5. Observe the displayed path | Selected file path shows internal system location like: /data/user/0/com.example.../download.jpeg | Only the filename (e.g., download.jpeg) or a friendly message like "File selected: download.jpeg" should be displayed | Bug_Fixed | Average | Screen Shot | Fixed |  | This could raise privacy or technical concerns, especially for non-technical users who don’t understand file paths. |  | 2025-06-26
B_ID_023 |  | Mobile Number> OTP verification flow | Flutter_Functional, UI/XI, Flutter_UI | No response after OTP verification | After entering a valid mobile number and submitting the OTP, no confirmation or success screen is shown. | 2. Go to the Home tab. 3. Tap the burger menu. 4. Navigate to "Reliability" section. 5. Enter valid mobile number. 6. Submit OTP sent to the number. | After submitting OTP, nothing happens—no screen change, success message, or redirection. | A success screen, toast message, or redirection to a relevant next screen is expected. | Bug | Major | Video Link | Not Fixed |  | There will be made redirect fileds when the API is implement |  | 2025-06-26
B_ID_024 |  | WhatsApp notification | Flutter_Functional, UI/XI, Flutter_UI | WhatsApp Notification Card Not Clickable | "WhatsApp Notifications" card and message under Reliability do not perform any action or redirect when tapped. | 1. Open the mobile app 2. Go to the Home tab 3. Tap on the Burger Menu 4. Tap on “Reliability” 5. Locate the “WhatsApp Notifications” card 6. Try tapping the card or message | Card appears static and does not respond to taps. | Tapping the card should either enable WhatsApp notifications or redirect to a relevant settings screen. | Bug_Fixed | Average | Screen shot | Fixed |  | it will be like this .It has been no screen |  | 2025-06-26
B_ID_025 | Home> Menu bar> Service Request | Service Request | Flutter_Functional | Missing Tabs for Accept/Not Accept Actions | After accepting or rejecting a request, the relevant success/failure tabs are not visible. | 1. Open the app 2. Go to Home tab 3. Tap burger menu 4. Select "Service Request" 5. Accept or Reject any request | No success or not accepted tab appears. | After accept → navigate to “Successful” tab After reject → show “Not Accepted” tab with reason input | Bug_Fixed | Average | Screen shot | Fixed |  |  |  | 2025-06-26
B_ID_026 |  |  | Flutter_UI | Header menus doesn't redirect or clickable | The "All Categories", "Nearby", "price","Top rated" not redirect and clickable | 1. Open the app 2. Go to Home tab 3. Tap burger menu 4. Select "Service Request" 5. Observe the header section | Header menus doesn't redirect or clickable ( "All Categories", "Nearby", "price","Top rated") | Should redirect with relavent content or fileds | Not Implemented | Critical | Screen shot | Not Fixed |  | There will be made redirect fileds when the API is implement |  | 2025-06-26
B_ID_027 |  | Service Request >filter | Flutter_UI | Price range accepts invalid input | The "Min Price" and "Max Price" fields accept any type of input, including letters/symbols | 3. Tap burger menu > Service Request 4. Tap Filter on the header 5. In the filter tab, input invalid values (e.g., text or symbols) in "Min Price" or "Max Price" fields | Price fields accept text, symbols, and special characters | Price fields should accept only numeric input and show validation errors if invalid | Bug_Fixed | Average | Video link | Fixed |  |  |  | 2025-06-26
B_ID_028 |  |  | Flutter_UI | Price range error handling message not show properly | In the service request, there is filter after redirect there have Price range error handling message not show properly | 3. Tap burger menu > Service Request 4. Tap Filter on the header 5. In the filter tab, input invalid values (e.g., text or symbols) in "Min Price" or "Max Price" fields | Price range error handling message not show properly | Price range error handling message should show properly | Improvements | Minor | Screen shot | Fixed |  | is not a bug vaidator text big thai's why Enter a valid non-negative....... |  | 2025-06-28
B_ID_029 |  |  | UI/XI, Flutter_Functional | Filter Redirects to Irrelevant Tab | After applying or resetting the filter, the app navigates to an unrelated tab instead of staying in the filtered results. | 1. Open Home tab 2. Tap Burger menu 3. Go to Service Request 4. Tap Filter on the header 5. Input necessary fields 6. Tap "Apply Filter" or "Reset" | Redirects to an irrelevant tab routing | Should remain on the filtered results screen or reset | Bug_Fixed | Average | Video link | Fixed |  | Wrong routing added |  | 2025-06-26
B_ID_030 | Create Account | 1. Full name 2. Date of birth 3. Zip code | Flutter_Functional | Fields accept invalid input | Full Name, Date of Birth, and Zip Code fields allow input of any characters without validation | 1. Open the mobile app 2. Go to Create Account 3. Enter invalid characters (e.g., @#$%, abc123) in Full Name, DOB, and Zip Code fields 4. Submit | Input is accepted and no error is shown for invalid characters | Input should be validated and show error messages for invalid formats | Bug | Average | Video Link | Fixed |  |  |  | 2025-06-28
B_ID_031 |  | Phone number > Optional | Flutter_Functional | Optional field throwing validation | "Phone Number (optional)" field incorrectly triggers a validation error when left empty. | 1. Open the mobile app. 2. Go to the create account 3.Leave the "Phone Number (optional)" field empty. | A validation error appears: “Please enter A phone number” | The form should be submitted successfully, as the "Phone number" field is marked optional. | Bug | Average | Video Link | Fixed |  |  |  | 2025-06-28
B_ID_032 |  | Step 2: Professional Details >Check box | Flutter_Functional | Form submits without accepting Terms & Privacy | The account creation form proceeds even if the Terms & Privacy Policy checkbox is unchecked | 1. Open the app and go to Create Account 2. Fill Step 1 (Basic info) 3. Proceed to Step 2 (Professional Details) 4. Do not check the agreement box 5. Tap Submit | Form is submitted without requiring the Terms & Privacy checkbox to be selected | Form should not be submitted unless the Terms & Privacy Policy checkbox is checked | Bug | Major | Video Link | Fixed |  |  |  | 2025-06-28
B_ID_033 |  | Step 2: Professional Details > About me | Flutter_Functional | About Me field exceeds limit | The "About Me" field indicates a 300 character limit in the placeholder text, but it allows the user to enter more than 300 characters without any restriction or error. | 1. Open the mobile app 2. Go to "Create Account" > Step 2: Professional Details 3. Enter more than 300 characters in the "About Me" field | User is able to input more than 300 characters in the field | User should be restricted to a maximum of 300 characters | Bug | Major | Video link | Fixed |  |  |  | 2025-06-28

## Test Cases
Test Result: | Passed | Failed | Need fix
| 0 | 0 | 0
Total: | 19
| Module | Test Description | Test Steps | Test Data | Expected Result | Actual Result | Status | Bug Screenshot